## Sheet1
Tasks | StartDate | End Date | Status
Project Team Formation | September 1st | September 10th | Done
Project Topic finalization | September 10th | September 15th | Done
Project Proposal | September 15th | September 18th | Done
Literature Survey | October 1st | October 9th | Done
Identify data traces and data preparation | October 10th | October 15th | Done
Preparing simulator algorithm | October 15th | October 25th | Done
Preparing progress report | October 26th | October 30th | Done
Identify regression methods | October 31st | November 5th | Pending
Several test and updating simulator code | November 6th | November 14th | Pending
Final experiment data report | November 15th | November 20th | Pending
Generate results and graphs | November 21st | November 30th | Pending
Final Project Report | December 1st | December 9th | Pending